## Slide 1
IEPD Registry & Repository
Courses of Action (COA)
3 August 2020

## Slide 2: Agenda
  Task Overview
  Assumptions
  Approach
  Hosting Options Analysis
  Solutions Criteria Narrowed
  Courses of Action (COA)
  Recommendation

## Slide 3: Task Overview
Conduct an analysis of platform hosting options for*:
      Public NIEM IEPD Registry
      Public NIEM IEPD Repository
      Restricted NIEM IEPD Repository
Make COA recommendations for IEPD R&R development and deployment
      Evaluated and considered several hosting platforms, and documented findings across multiple criteria for comparison
      Narrowed recommendations to viable options
            * System Requirements Specification (SRS) documents requirements
Notes: While its not required for the public registry to be the public repo, it makes sense to try to do it that way
System Requirements Specification (SRS)
  Produced by the NBAC R&R Tiger Team
  Feedback from across the NIEM community
  Source: DI2E site
Dialogue with NMO leadership

## Slide 4: Assumptions
Funding
  FY20 funding $448.5K
  $300K/year follow-on funding thru FY2025
Scope
  Develop Registry & Repositories
  Align with larger NIEM tool modernization effort
  Majority of security controls inherited from hosting platform (e.g., RMF)
Approach
  Phase I: fulfill requirements of SRS (basic IEPD submission/download, search); requires manual IEPD validation by administrators
  Phase II: integrate with BAH tool suite, advanced search, best practices web development
Functional
  Average usage low (< 10 concurrent users)
  10GB server space
Notes: Additional functional assumptions:
  Tools need to be available to enable efficient inspection and re-use of artifacts particularly subset and extension schema
  May have increased usage during training sessions
A restricted repository requires
  Identity management
  Authentication and access controls
  Rules governing assignment of roles and privileges for enterprise search and discovery
  IEPD registration
The development of new software will be open-source
Development efforts will seek to balance community needs against complexity and cost in a phased and modular approach with updates/modules released on an independent schedule as completed
The develop of NIEM R&R will support native integration with NIEM IEPD tools as defined in the NIEM Tool strategy.
Privileges are defined and built on each of the three entities
  Public Repository: Anonymous users/registrants are able to access the repository and delete, upload and download IEPDs.
  Public Registry: Registrant has the option to restrict sensitive information from being displayed to the User (Search Customer), such as Point-of-Contact (POC) information or Uniform Resource Locater (URL) or Uniform Resource Identifier (URI).
  Restricted Registry: places a premium on identity and access controls that guarantee the proper access of potential subscribers to Repository equities. As such, the Restricted Repository imposes more comprehensive requirements on mandatory disclosure of User information (User profiles) and documentation of IEPD registration metadata than in the case of the NIEM Public Registry.
Assertions
  Iterative
  Coding: Majority of work performed by single developer with support from others as needed
  Scope: IEPD Repository & Registry (R&R) will be integrated with NIEM Tool Modernization capabilities
    Degree of coupling is currently unknown and will be determined over time and approved by the Government
  Agile/DevSecOps; incremental delivery
  Communicate progress frequently with NMO leadership/project stakeholders

## Slide 5: APPROACH
Phase I: Baseline capability
  Meets requirements of the SRS
  Basic IEPD submission, download, and search
  Limited by time, funding, and platform limitations
  Does NOT work with data “inside” an IEPD—requires user to download an IEPD and manipulate locally
  Requires manual IEPD inspection & validation by administrators
Phase II: Advanced capability
  Capabilities beyond the SRS, currently unspecified
  Informed by Phase I lessons learned/experience
  Integration with BAH tool suite (e.g. search/retrieve/post API)
  Resolve gaps based on Phase I platform/time limitations
  Best practices web development (e.g. Containerization, deployable in any environment, Open-source code)
Notes: SRS does not go into detail on how to work with IEPDs and the internal components of IEPDs
  Treats IEPDs as “blobs”
Phase I requires tool support for the administrator/IEPD inspection/validation function
  Use Oxygen to validate XML, schemas, and NIEM NDR rules, and the MPD catalog, validate sample instances, and other artifacts internal to the IEPD
  Currently there is NO tool to validate IEPDs against the MPD spec
  w/o new tools, there will be low confidence in the validation of IEPDs
  Tools could be used by IEPD developers, Administrators wh
Leveraging existing sites (e.g. niem.gov, DOJ Clearinghouse, WMA-AFIP) does not support software reuse for Phase II
en validating IEPDs, and BAH tool team

## Slide 6: Hosting Options Analysis
Market Research for Hosting
Criteria Analysis
Website Hosting
Security/RMF
Cost Structure
Custom software restrictions
Ease of Development & Control
    Containerization Support
    Control over Deployments & Updates
    Level of Administrator Access
    User Access Control Limitations
  Handling of sensitive data (e.g., CUI, privacy)
Audit capability​
Backups
NIEM.gov​
DOJ Clearinghouse​
MAX.gov​
APAN​
CKAN​
Intelink​
GovCloud/MilCloud
DI2E (Defense Intelligence Information Enterprise)
DoD Federated Architecture Portal
Amazon Web Services-Commercial (AWS)
AWS GovCloud
Hosting Options Narrowed
Platforms | Public Registry | Public Repository | Restricted Repository | Phase II
NIEM.gov |  | ? |  | 
DOJ Clearinghouse |  |  |  | 
DoD Federated Architecture Portal |  |  |  | 
AWS |  |  |  | 
AWS GovCloud |  |  |  | 
Notes:   Voice over that can substitute other cloud platforms/providers for AWS
  See spreadsheet for more details about criteria and responses from platforms
  Ease of Development
    Containerization Support
    Control over Deployments & Updates
    Level of Administrator Access
    User Access Control Limitations

## Slide 7: Solutions Criteria Narrowed
Platform | Website Hosting | Cost Structure | Ease of Development & Control | Security/ RMF | Custom software Restrictions
NIEM.gov | Public Registry / Repository only | DHS absorbs development and hosting costs | Design control Low Development control Low Update/Deployment Low control | Inherits security controls from niem.gov | Limited to Drupal Limited to MySQL/MariaDB
DOJ Clearinghouse | Public Registry / Repository only | DOJ absorbs development and hosting costs | Design control Low Development control Low Update/Deployment Low control | Inherits security controls from Clearinghouse | Limited to .NET Framework Limited to SQL Server
DoD Federated Architecture Portal | Restricted Repository only | DDC5I absorbs development and hosting costs | Design control Med Development control Med Update/Deployment Med control | Inherits security controls from WMA-AFIP | Limited to .NET Framework Limited to SQL Server
AWS | Both | Pay per usage, but other cost models available | Design control High Development control High Update/Deployment High control | Security configuration required | No language restrictions Allows open source software No DB limitations
AWS GovCloud | Both | Probable 20-40% premium over commercial AWS | Design control High Development control High Update/Deployment High control | Additional security solutions available compared to AWS | Same as AWS Some minor limitations
Notes: Website Hosting:
Cost Structure:
NIEM will consider custom code
The DoD FAP doesn’t have web hosting and doesn’t support containers.
NIEM team can't write new code and deploy to WMA server instances on NIPR (but public facing) and SIPR. DISA provides OS (windows server 2016), SQL server (SQL server 2016). AID provides web code (VisStudio 2019, .Net 4.8) .Net
CSS, AJAX. Must have Federal CAC /PIV
Control of deployments relate to access control

## Slide 8: phase I Courses of Action
Course of Action (COA) and Related Activities
COA 1 Donated labor (on existing site) Leverage DOJ Clearinghouse or niem.gov for Public IEPD Registry/Repository Leverage WMA-AFIP for Restricted IEPD Registry/Repository Platform may limit functionality
COA 2 New site Cloud-enabled environment; non-proprietary source code; under NMO control Platform will not limit functionality
COA 3 MVP w/donated labor, build new site Leverage DOJ Clearinghouse or niem.gov for MVP for public Registry/Repository Leverage WMA/AFIP for MVP for restricted Registry/Repository Further development cloud-enabled, open source, under NMO control
Notes: For every COA, first deliver an MVP, then add additional functionality in subsequent deliveries to meet SRS
For COA3, expect only one delivery—the MVP

## Slide 9: IEPD R&R
COA 1 Donated labor (on existing site) Leverage DOJ Clearinghouse or niem.gov for Public IEPD Registry/Repository Leverage WMA-AFIP for Restricted IEPD Registry/Repository Platform may limit functionality | 
Advantages + Phase 1 hosting costs donated + Security controls / RMF / compliance baked into existing sites + May free some labor to support separate tooling for administrators | Disadvantages - Existing platforms limit requirements / functionality - May not integrate with Tool Modernization effort (i.e. web services) Donated labor limits NMO control over features, level of effort Requires PIV certificate for user access to restricted repo
Contributors: NMO, DHS or DOJ, JS J6, GTRI Timeline: 3-12 months Risk: Depends upon DHS/DOJ/J6 in-kind contribution May not meet all IEPD R&R requirements | 
Notes: COA1 falls back to COA 2 if donated labor doesn’t happen

## Slide 10: IEPD R&R
COA 2 New site Cloud-enabled environment; non-proprietary source code; under NMO control Platform will not limit functionality | 
Advantages + Under NMO control — Not dependent on donated labor + Open source, cloud-enabled, deployable anywhere + Meets all requirements; functionality not limited by platform; supports web services for tools integration + Developed via agile / DevSecOps delivery + Provides base platform for Phase 2 | Disadvantages - Delayed start for hiring site developer - Responsible for hosting cost in Phase 1 Must implement security controls / RMF / compliance Long-term sustainment costs
Contributors: NMO, GTRI Timeline: 6-12 months Risk: Delayed start due to hiring; compliance & security increase LOE | 
Notes: COA 2 New site Cloud-enabled environment; non-proprietary source code; under NMO control
Platform will not limit functionality
COA2A: leverage DOJ Clearinghouse for Public Repo (vice using niem.gov)
COA2B: have Lanzo/Aubrey develop Public Repo using APAN

## Slide 11: IEPD R&R
COA 3 MVP w/donated labor, build new site Leverage DOJ Clearinghouse or niem.gov for MVP for public Registry/Repository Leverage WMA/AFIP for MVP for restricted Registry/Repository Further development cloud-enabled, open source, under NMO control | 
Advantages + Engages partnerships for MVPs + Meets all requirements; functionality not limited by platform; supports web services for tools integration + New site open source, cloud-enabled + New site developed via agile / DevSecOps delivery + Provides base platform for Phase 2 | Disadvantages - Dependent on donated resources for MVP - Responsible for hosting cost in Phase 1 - "Do both" replicates labor in Phase 1 Must implement security controls / RMF / compliance Long-term sustainment costs
Contributors: NMO, DHS or DOJ, JS J6, GTRI Timeline: 3-12 months Risk: Compliance & security increase LOE; donated resources may fall through | 
Notes: COA 3 MVP w/donated labor, build new site
Leverage DOJ Clearinghouse or niem.gov for public Registry/Repository
Leverage WMA/AFIP for restricted Registry/Repository
Cloud-enabled environment; non-proprietary source code; under NMO control

## Slide 12: NMO Recommendation
Recommend: COA 1 Donated labor (on existing site) Leverage DOJ Clearinghouse or NIEM.gov for Public IEPD Registry/Repository Leverage WMA-AFIP for Restricted IEPD Registry/Repository Platform may limit functionality | 
Timeline: 3-12 months ESC Decision: ___Approve ___Disapprove If approved, next steps: Establish agreement between NMO and other contributors Stand-up working group and develop work plan Implement MVPs on existing sites (public and restricted) | 
Notes: Voice over: discuss plan for improvements after MVPs delivered

## Slide 13: End

## Slide 14: GTRI Phase I activities (COA 1)
  Work with development team from existing sites (e.g. DHS, DOJ, JS J6) to ensure web site upgrades meet SRS requirements
  Participate in testing before upgrades go live
  Develop software to support IEPD inspection and validation
    Used by NMO administrators to validate submitted IEPDs meet compliance specifications
  Begin planning for Phase II activities